## Transition Black Isle
Outcome - Partner Specific | What | Targets | When | Who Else? | Lead? | Staffing | Budget
2.6 We will partner with Community Resources Network Scotland to promote the work of their re-use, repair and recycling members in Highland including creating new drop off points to make it easier for people to donate household goods and simpler for charities to collect them. | Project/ Service | Drop off points established | From Y1Q4 | T/S/U/BI |  | 1 Project Officer (TBC) - New |  | YEAR 1 | YEAR 2 | YEAR 3 | TOTAL
3.1 Engaging events (online and face to face) to demonstrate attractive and achievable ways to reduce food waste. Drawing on best practice and with support from Zero Waste Scotland (ZWS), we’ll provide engaging sessions on menu planning, portion sizes, cooking with leftovers, storing food, understanding expiry dates and managing your fridge and larder. Through Velocity’s connections with the NHS and social prescribing, we’ll tie this strand of work in Inverness closely to the health and family agendas. | Event | 111 events, 8010 participants. | From Y1Q2 | All/T/L/BI | L |  | staff costs | 31491 | 31963.365 | 32442.8155 | 95897.1805
3.2 Share ideas, tips, challenges and stories online and through local media to help people reduce food waste. We’ll ask Highland families to ‘take the food waste challenge’, support them to make changes and share their stories widely. | Programme | Bi-weekly to over 10,000 fb followers | From Y1Q2 | All/T/L/BI | L |  | office costs | 1000 | 1015 | 1030.225 | 3045.225
4.3 Pilot use of re-usable containers in take-aways and community-run ‘meals on wheels’ services. Thurso CDT will pilot in their community meals programme and share learning with other similar services across Highland. | Project/ Service | Pilots complete & learning shared | End Y2 | T/S/BI/I/FW |  |  | major purchases | 10000 | 10150 | 10302.25 | 30452.25
4.8 Other action including: expanding use of reusable nappies, an Inverness GP practice piloting reduction of PPE waste and an initiative on Skye to re-use cardboard on the island for growing, packaging and fuel. | Project | various | From Y1Q1 | L/S/BI/I/FW |  |  | materials | 2000 | 2030 | 2060.45 | 6090.45
Outcome - All | [6 empty] | public engagement | 2000 | 2030 | 2060.45 | 6090.45
1.1 Climate conversations and cafes. From structured discussions to drop-in cafes, we will create opportunities for people to learn, explore and discuss the climate emergency and sustainable consumption in face to face and online settings. Many conversations will be run with other groups and networks including parent’s groups, men’s groups, WRI, youth groups, community councils, faith communities etc. | Event | 200 events engaging 4000 people | From Y1Q1 | All |  |  | travel | 1000 | 1015 | 1030.225 | 3045.225
1.2 Engaging young people. Working with High Life Highland, the Highland Youth Parliament and other youth networks we will train youth climate champions, support them to take action on sustainable consumption and maximise their involvement in all aspects of our project. | Programme | 200 youth champions | 50 yr 1, 100 yr 2, 50 yr 3 | All/KSB |  |  | other | 0 | 0 | 0 | 0
1.3 Film nights and discussions. We’ll curate a programme of engaging films on climate and consumption and facilitate discussion to stimulate reflection and action. Some will take place locally but many will be online and available to people across the Highlands. | Event | 118 film nights, 2690 participants | From Y1Q1 | All |  |  | Total | 47491 | 48203.365 | 48926.4155 | 144620.7805
1.4 Highland sustainable consumption community. We’ll build a vibrant online community to foster collaboration and the exchange of information and ideas on climate and consumption. We’ll share practical ideas, showcase initiatives from across the Highlands and beyond. This will be a key strand of building a climate movement in Highland that will continue beyond the life of the project. | Comms/ Engagement | 2000 people | From Y1Q1 | All
1.5 Out and about. We’ll take our messaging, resources, ideas and tips out into the community through a strong presence at local galas, events and wherever people meet, whether online or physically. | Comms/ Engagement | 58,750people | From Y1Q2 | All
1.6 Reaching widely through local media. We’ll share top tips and inspiring stories of ordinary people making a difference through local radio, TV, papers and community online groups. Our partnership has a collective fb following of 24,000 and connections with local traditional media with a combined audience of over 2 million. | Comms/ Engagement | 1 million reach social, 3 million reach traditional. | From Y1Q1 | All/KSB
1.7 Signpost to advice and support on other climate change issues. The project will stimulate interest in responding to climate change beyond the project’s focus on consumption. We will develop referral routes to connect people to further information on issues such as home and community energy, active travel, climate adaptation and low carbon food. | Programme | Complete | From Y1Q4 | All
2.1 Grow networks for sharing stuff. Sharing stuff is already a part of Highland culture. We’ll grow this by building and extending local online sharing communities using existing platforms such as community Facebook groups and apps like freecycle, gumtree and streetbank. | Project/ Service | 25% increase from baseline | From Y1Q2 | All
2.3 Highland repair directory. We will create an online directory of highland-wide repair skills, resources, courses and events so that people can find or develop the skills needed to repair rather than replace. | Project/ Service | Complete | By Y2Q3 | All/U
2.4 Pop up swishing events and zero waste fairs. We will run regular swishing, swapping and zero-waste events and use these as an opportunity to highlight links between consumption and climate change. We’ll encourage and support other community organisations to run their own events, for example Parent Councils (uniforms). | Event | 111 events, 9880 participants | From Y1Q2 | All
2.5 Explore and pilot new models of shared car use. Many people in the Highlands need to use a car but not everyone needs to own one. New platforms allow people to hire their cars out to others. With advice from COMOUK, we’ll promote these new approaches to car sharing, monitor uptake and share learning. | Project/ Service | Pilots completed and learning shared | From Y1Q2 | All
3.1 Engaging events (online and face to face) to demonstrate attractive and achievable ways to reduce food waste. Drawing on best practice and with support from Zero Waste Scotland (ZWS), we’ll provide engaging sessions on menu planning, portion sizes, cooking with leftovers, storing food, understanding expiry dates and managing your fridge and larder. Through Velocity’s connections with the NHS and social prescribing, we’ll tie this strand of work in Inverness closely to the health and family agendas. | Event | 111 events, 8010 participants. | From Y1Q2 | All/T/L/BI
3.2 Share ideas, tips, challenges and stories online and through local media to help people reduce food waste. We’ll ask Highland families to ‘take the food waste challenge’, support them to make changes and share their stories widely. | Programme | Bi-weekly to over 10,000 fb followers | From Y1Q2 | All/T/L/BI
3.3 Work with local businesses to reduce food waste. We’ll run workshops in partnership with Highland Tourism, Highland Regional Food Group, Business Chambers and ZWS to help businesses reduce food waste and distribute near-date food. | Event/ Programme | 100 businesses per year | From Y1Q3 | All/HGFP
3.4 Increase home composting. Via practical workshops, information and advice online, provision of subsidised compost bins and food caddies and, in collaboration with local Men’s Sheds, construction of composters from re-used timber. | Event | 84 events with 2590 participants | From Y1Q2 | All/FW
3.5 Explore and report on the feasibility of community-scale composting. Building on significant partner experience we will engage with Highland Council and Zero Waste Scotland to investigate the feasibility of community-scale composting in the Highlands. | Project/ Service | Report complete. | end Y2 | All/ FW/ HGFP
4.1 Increase availability and uptake of packaging-free retail opportunities in local shops. Two of our implementing members will do this in their own shops but our main focus will be to accelerate the uptake of these approaches in local shops, building on learning from this recent initiative. | Project/ Service | 30 new businesses offering refill | From Y1Q2 | All/T/HGFP lead.
4.2 Increase availability and uptake of re-use options for ‘on the go’ food and drink including water refills, re-usable cups and lunch boxes. We’ll support covid-safe practice, encourage businesses to register their services with the refill app and work with our tourism partners to promote their use. | Project/ Service | 100 new businesses | From Y1Q2 | All/ HGFP lead.
4.5 Work with local businesses and networks to develop a new Zero Waste Highland business charter similar to this proven model and promote businesses that are actively reducing packaging and waste. | Programme | 300 businesses | Y2&3 | All
4.6 Establish a Highland-wide single use cup collection and re-cycling scheme, building on KSB’s experience in Glasgow. While our focus will be on re-use, we want to close the loop on single use cups and see this is an ‘entry-level’ action with significant public engagement potential. | Project/ Service | 100,000 cups diverted from landfill | Y1,2&3 | All
4.7 Mobilise local communities and businesses to work with industry bodies to improve the re-cycling of significant rural industry plastics including marine (in partnership with fishingforlitter), silage wrap and tree shelters. | Project | Industry bodies engaged and learning shared. | From Y1Q2 | All