PDay 2018 Planning Meeting Tues 21 Nov    Revised, meeting 31 January

Present:  Duncan, Lesley, Penny, Jimmie, Julie

Apologies: Peter, Trish

- Decisions made:-

| Potato Delivery storage Pre PD Leftovers after the Day | a) To be stored by James Dingwall b) stored at Duncan Scott’s | ACTION Julie to liaise nearer time re delivery detail. | Review In hand. |
| --- | --- | --- | --- |
| Congestion feedback from last year Hall layout Sales points Advertise 2 timings again 11-1pm, 1.30-3pm | Decisions to alleviate:- Fewer potatoes so more space No veg/bread stalls - increase space Move sales points to beside the door – see hall plan |  |  |
| Onions Paper bags Potato Grow bags Hessian bags Compost Plastic yogurt pots for onion sales | 2 varieties of onions (1 red, 1 white), no shallots Yes, same again Yes Yes No, but point people to it | Julie – let M+T know Julie – order again, 500 – better quality/size Julie – research and order Duncan - research Include on handout given on entry | Ordered. Done – surplus box from Dan Ross. Trish has done this – supply arrived. Anne T also has some leftover from last year. Done – agreed he will order 100 Include on handout given on entry – Penny All to collect. 500g size |

- Tasks

Pre P. Day

| Area | Detail | When | Who | Review |
| --- | --- | --- | --- | --- |
| Hall booked |  | Done |  |  |
| Potato ordering | Incl orders from Soirbheas, TTF, Beauly, Dan Ross | Dec-Jan | Trish and Maggie | In hand. |
| Potato donations | Grewars, Drumderfit, Resolis |  | Peter to liaise Maggie and Trish respectively | Done |
| Advertising | Newsletter – first mention Poster to poster people, on website Poster in newsletter Newspaper/ ICA ? Facebook | Dec Late Jan End Jan, Feb End Feb | Nov as no newsletter end of Dec. Done. Julie liaise with Comms group | Done Done Done Done |
| Handout - on entry | Poss A5 size, incl map of hall, price list …….. |  | Penny | In hand |
| Volunteer Rota |  |  | Julie | In Hand |

Potato Day

| Area | Detail | When | Who | Review |
| --- | --- | --- | --- | --- |
| Hall set up | Tables out and boxes on | On the day | Jimmie Hepburn – Lead | Boxes needed. Anne has 20. All to collect. |
| Signage and sundries needed | Entry door – entry price, how to pay Hall – on potato variety boxes, above tables (First Earlies etc), Sales Points, Experts Point Sales Points price lists Cash boxes, pencils, blutac, Sellotape, staplers, scissors, cash bags |  | Peter | Penny – info handout in hand Signs – some kept from last year, Peter making those we still need. Air bricks for sign canes – Peter done To be collected prior to event – Julie + anyone else |
| Oversee transportation of potatoes | 2 trailer and 2 barrows | On the day | Duncan - Lead | Duncan and Peter – trailers; Jimmie’s if needed. James Dingwall transport tatties there; we transport leftovers to Duncans |
| Catering | Kitchen and cafe |  | Lesley Lead + 2 (2 in Morn, 2 in afternoon) + 1 vol for wash-up | In hand + email to go out re cake contributions |
| Door | Manage entry process, monitor numbers (Hall capacity 200) | On the day |  | Julie oversee on day – rota to include this also |
| Parking ? |  |  |  | Decided not to monitor. |
| Experts |  |  | Trish and Maggie | Done |
| Monitoring potatoes | Ensure quality, sift out bad, ensure topped up. Ensure half kept back for afternoon session. Tally quantity at beginning of day, and tally at end of day before transport to D’s | On the day | Jimmie Lead, Duncan assist Duncan Lead at end of day. | Lists of potatoes to Jimmie and Duncan for monitoring purposes. Julie to forward when order finally confirmed. |
| Money gathering during day, general monitoring | Periodically collect money from sales points, café, and entry door. |  | Julie |  |
| Seed Swap table |  |  | Seed swap group members | Clive and Julie |

Post P.Day

| Coordinate leftover deliveries |  |  |  |
| --- | --- | --- | --- |
| Income tallying |  |  | Julian |