## Sheet 1
January 2023 - HCWP Update for TBI Admin Team
| Developments | Next steps | Decision Points
Outcome 1: Increased public understanding of how unsustainable consumption choices and patterns contribute to climate change. This is an important motivator for engaging people in the practical actions outlined under outcomes 2,3 & 4.
1.1 Climate conversations and cafes. From structured discussions to drop-in cafes, we will create opportunities for people to learn, explore and discuss the climate emergency and sustainable consumption in face to face and online settings. Many conversations will be run with other groups and networks including parent’s groups, men’s groups, WRI, youth groups, community councils, faith communities etc. | Becky Richmond BIP undertook “SCCAN Climate Knowledge into Climate Action” training in December. Hope to collaborate and tie HCWP Climate Conversation objectives in to Place plan/ Black Isle Tourism consultation activities/clinics. | Meet with Mari Todd UHI Psychology lecturer in Avoch also interested in Climate conversations. Climate Conversation session for HCWP delivery team coming up. | Do the admin team support trying to tie-in with the place plan consultation by Black Isle Partnership to try to embed our activity beyond 3 years? Any issues anticipated?
1.2 Engaging young people. Working with High Life Highland, the Highland Youth Parliament and other youth networks we will train youth climate champions, support them to take action on sustainable consumption and maximise their involvement in all aspects of our project. | Keep Scotland Beautiful first sessions of Youth Climate Advocate training starting now (11 to 21 years olds) led by Ellie on the HCWP delivery team. At the end of training, they take pledge to make changes / volunteer for HCWP. Have highlighted to D of E lead at Fortrose Academy and Scouts as it counts towards credits. | Talk to academy about rolling out. Within school for Saltire award and how best to get kids to volunteer for HCWP. Laura/myself may need to get dedicated PVGs to participate. Starting point for volunteering would be with repair cafe / HCWP stand at the markets. | Do the Admin team support this approach? Are there any other areas within TBI that would suit having volunteers from the academy once we know the process and structure required? E.g. D of E, Saltire Award, Scout sessions?
1.3 Film nights and discussions. We’ll curate a programme of engaging films on climate and consumption and facilitate discussion to stimulate reflection and action. Some will take place locally but many will be online and available to people across the Highlands. | Ongoing. | Discuss films within delivery team. Book dates with Cromarty Cinema / Muir of Ord Hub / Screen machine for local halls - Tie in with opportunity for Climate conversations.
1.4 Highland sustainable consumption community. We’ll build a vibrant online community to foster collaboration and the exchange of information and ideas on climate and consumption. We’ll share practical ideas, showcase initiatives from across the Highlands and beyond. This will be a key strand of building a climate movement in Highland that will continue beyond the life of the project. | HCWP Social Media, KSB led, we share their content.
1.5 Out and about. We’ll take our messaging, resources, ideas and tips out into the community through a strong presence at local galas, events and wherever people meet, whether online or physically. | Repair Cafes currently our strongest face to face presence for HCWP. Hope to tie in with Black Isle Tourism clinics / Place Plan Clinics. | Want to develop display materials for both repair cafes and markets. Meet with market organisers, see what is possible/practical. Engagement would need to be quantifiable to count towards our engagement targets.
1.6 Reaching widely through local media. We’ll share top tips and inspiring stories of ordinary people making a difference through local radio, TV, papers and community online groups. Our partnership has a collective fb following of 24,000 and connections with local traditional media with a combined audience of over 2 million. | Repair Cafe volunteers forming “publicity” working group for better support with this. Lots of potential for further publicity around consumption/attracting people to our events for repairs / to talk to us about what else TBI/HCWP do. | Use repair cafe data to get some good statistics now we have had 3 full cafes recording data properly.
1.7 Signpost to advice and support on other climate change issues. The project will stimulate interest in responding to climate change beyond the project’s focus on consumption. We will develop referral routes to connect people to further information on issues such as home and community energy, active travel, climate adaptation and low carbon food. | Ongoing via social media. | Circular Communities Scotland have a Marketing 101 Social Media Coaching session in February that Laura and I intend to attend.
Outcome 2: Increased use of pre-loved, repaired and shared goods.
2.1 Grow networks for sharing stuff. Sharing stuff is already a part of Highland culture. We’ll grow this by building and extending local online sharing communities using existing platforms such as community Facebook groups and apps like freecycle, gumtree and streetbank. | Black Isle Freebies, Facebook Marketplace, Black Isle Noticeboard - all strongly supporting this virtually. TBI “library of things” (aside from the apples press) has been expanded with the gazebos we bought for the Highland Climate Festival at Avoch but it would be good to build on this. The gazebos could be made available for other community groups. Currently stored in the Chanonry Scouting Shed next to the Fortrose Free Church/village hall. One members top items for their “library of things” on Circular Economy Scotland’s Repair and Share network was: 1. Thermal Imaging Camera (mainly because a local volunteer takes it out to do home audits) 2. Apple Press 3. Electric Strimmer 4. Video Projector (mostly local groups borrowing for meetings and events) 5. Corded Circular Saw 6. Garden Shredder 7. Gazebo 8. Pallet Breaker 9. Folding Tables 10. Extendable Loppers | Hope to encourage a culture of swapping / selling secondhand by meeting to exchange at our Repair Cafes / Markets rather than individual journeys. Will let other local community groups know we have gazebos available as we go. Hope to talk to Highlife Highland about libraries having non-book items that can be borrowed. | Does the admin team thoughts for the future on expanding TBI’s Library of things?
2.2 Repair and upcycling workshops. We will run a range of practical workshops, physically and online to build skills in repairing, re-making and upcycling. | Working group for workshops formed, hope to use venues that support local repair businesses / existing events like repair cafe / markets: Visible mending Get to know your sewing machine Tool sharpening simple bike maintenance Seasonal repairs - e.g. Xmas lights (for next year now) Possible Mens Shed Clinic for longer repairs Swishing events (swapping things you don’t need/want for ones you do) | Schedule and book venues with repair cafe contacts/ repair businesses for collaboration.
2.3 Highland repair directory. We will create an online directory of highland-wide repair skills, resources, courses and events so that people can find or develop the skills needed to repair rather than replace. | Continue gathering information about local business, crafters, individuals offering repair. | Encourage them to partner with Repair Cafe / workshops
2.4 Pop up swishing events and zero waste fairs. We will run regular swishing, swapping and zero-waste events and use these as an opportunity to highlight links between consumption and climate change. We’ll encourage and support other community organisations to run their own events, for example Parent Councils (uniforms). |  | Talk to academy about pupil involvement. Avoch Primary keen to get Academy parents involved in second hand toy sale to attract items suitable upper level of primary. Academy did Christmas Prom Swish and interested in cost of living activities like second hand sales. Rose and Laura to contact key school contacts.
2.5 Explore and pilot new models of shared car use. Many people in the Highlands need to use a car but not everyone needs to own one. New platforms allow people to hire their cars out to others. With advice from COMOUK, we’ll promote these new approaches to car sharing, monitor uptake and share learning. | No-one could attend COMO conference but Keith Masson potentially interested in these topics “as a Black Isler” ( Head of Net Zero Transition HIE) | Kick off meeting for HCWP. Signpost to Community Councils.
2.6 We will partner with Circular Communities Scotland to promote the work of their re-use, repair and recycling members in Highland including creating new drop off points to make it easier for people to donate household goods and simpler for charities to collect them. | Kick off meeting imminent. Keen to collect more items at markets and repairs cafe (and promote). | Kick off meeting for HCWP. “Informal recycling networks” - of residual recycling (outwith blue bin). Liaise with Highland Council on information we can use in our display, Terracyle. Promote existing local drop off points.
Outcome 3: Reduced food waste and lower emissions related to residual food waste.
3.1 Engaging events (online and face to face) to demonstrate attractive and achievable ways to reduce food waste. Drawing on best practice and with support from Zero Waste Scotland (ZWS), we’ll provide engaging sessions on menu planning, portion sizes, cooking with leftovers, storing food, understanding expiry dates and managing your fridge and larder. Through Velocity’s connections with the NHS and social prescribing, we’ll tie this strand of work in Inverness closely to the health and family agendas. | Kick off meeting imminent. Laura to be given Love Food Hate Waste supporting materials, posters, freezer clips, recipe cards, spaghetti measurers and fridge thermometers.
3.2 Share ideas, tips, challenges and stories online and through local media to help people reduce food waste. We’ll ask Highland families to ‘take the food waste challenge’, support them to make changes and share their stories widely. | Kick off meeting imminent.
3.3 Work with local businesses to reduce food waste. We’ll run workshops in partnership with Highland Tourism, Highland Regional Food Group, Business Chambers and ZWS to help businesses reduce food waste and distribute near-date food. | To be promoted via Black Isle Tourism. Led by Highland Good Food Partnership within HCWP.
3.4 Increase home composting. Via practical workshops, information and advice online, provision of subsidised compost bins and food caddies and, in collaboration with local Men’s Sheds, construction of composters from re-used timber.
3.5 Explore and report on the feasibility of community-scale composting. Building on significant partner experience we will engage with Highland Council and Zero Waste Scotland to investigate the feasibility of community-scale composting in the Highlands. | RAA interested in community composting. | Present HCWP to RAA, explore funding opportunities with Highland Climate Hub. Plus future potential for tying in with sharing shed/Rosemarkie Allotments. | Does the admin team support a collaboration with the RAA and also seeking joint funding from the Highland Climate Hub.
3.6 Increase uptake of separate food waste collection in Inverness area. Around 60% of domestic food waste in Inverness goes in the general bin. In partnership with Highland Council we will engage local community leaders and networks in the city to identify barriers and encourage more people to recycle food waste. | N/a
Outcome 4: Reduce single-used items and unnecessary packaging and improve recycling of residual. ‘Reduce’ activities will engage with local businesses to advocate for change, share good practice and provide technical support. We’ll also engage with consumers to stimulate the market for alternatives. KSB & ZWS will provide technical support across much of this activity and we’ll tie many of these activities together through activity 4.5.
4.1 Increase availability and uptake of packaging-free retail opportunities in local shops. Two of our implementing members will do this in their own shops but our main focus will be to accelerate the uptake of these approaches in local shops, building on learning from this recent initiative. | Black Isle Tourism will help keep businesses in the loop where relevant for TBI | Visit Dingwall’s Wyvis Refills & Eco Essentials and also understand other refills presence at Black Isle Markets for this sort thing so we don’t tread on any businesses toes.
4.2 Increase availability and uptake of re-use options for ‘on the go’ food and drink including water refills, re-usable cups and lunch boxes. We’ll support covid-safe practice, encourage businesses to register their services with the refill app and work with our tourism partners to promote their use. | Black Isle Tourism will help keep businesses in the loop where relevant for TBI. Velocity have been trialling 40p premium on single use takeaway cups and selling branded re-usable glass travel cups and metal lunchboxes - sharing their learning. | Aim to encourage all Black Isle Hospitality businesses to engage with HCWP topics. Aim to offer online webinar to share Velocity’s learning with Black Isle hospitality businesses. Beach Cafe Interested. We could suggest Black Isle Tourism branded items and get bulk discount?
4.3 Pilot use of re-usable containers in take-aways and community-run ‘meals on wheels’ services. Thurso CDT will pilot in their community meals programme and share learning with other similar services across Highland. | Black Isle Tourism will help keep businesses in the loop where relevant for TBI | Aim to encourage all Black Isle Hospitality businesses to engage with HCWP topics.
4.4 Pilot a Deposit Return Scheme for re-usable cups in ‘closed-loop’ context e.g. festival, event or large institution. | Black Isle Tourism will help keep businesses in the loop where relevant for TBI. “Highland Cup Movement” being investigated for NC 500. | Aim to encourage all Black Isle Hospitality businesses to engage with HCWP topics.
4.5 Work with local businesses and networks to develop a new Zero Waste Highland business charter similar to this proven model and promote businesses that are actively reducing packaging and waste. | Black Isle Tourism will help keep businesses in the loop where relevant for TBI. A lot of charters around. Black Isle Tourism interested in local one too. | Aim to encourage all Black Isle Hospitality businesses to engage with HCWP topics.
4.6 Establish a Highland-wide single use cup collection and re-cycling scheme, building on KSB’s experience in Glasgow. While our focus will be on re-use, we want to close the loop on single use cups and see this is an ‘entry-level’ action with significant public engagement potential. | Black Isle Tourism will help keep businesses in the loop where relevant for TBI. KSB is leading this. | Aim to encourage all Black Isle Hospitality businesses to engage with HCWP topics.
4.7 Mobilise local communities and businesses to work with industry bodies to improve the re-cycling of significant rural industry plastics including marine (in partnership with fishingforlitter), silage wrap and tree shelters. | This might end up falling under 2.6 as one of the members does this sort of recycling in the Highlands. | Aim to encourage all Black Isle Hospitality businesses to engage with HCWP topics.
4.8 Other action including: expanding use of reusable nappies, an Inverness GP practice piloting reduction of PPE waste and an initiative on Skye to re-use cardboard on the island for growing, packaging and fuel. | The Nappy Network has petered out simply due to being run by volunteer parents of babies who then grew out of nappies etc. | Investigate whether we could support The Nappy Network in trying to find replacement trustees / volunteers and then helping to promote via local doctors surgeries / baby groups. Assistance in getting funding? | Any creative suggestions for enabling expansion of re-usable nappies?